## INCOME
PROBLEMS: BASIC IDENTIFICATION
What Problem? | Incidence: Who What Where is affected ? | Consequences of that Problem? | Responses? Mitigation? Treatments? | Other Aspect?
Collected rainfall data is not represent to all project villages | Difficult o make size calculation of water supply facilities construction and renovation | Over size and undersize / cost
Land ownership for water supply facility construction | Some necessary land are individual own / govt. own | Difficult to get agreement / authorisation for water supply facilities implementation
No potential water resources for water supply facilities construction | No more water for agri and livestock | No increased production | Alternative livelihoods system should be considered. | Use better water management system (use less water option).
Cost of possible solution of water supply facilities is high
Sense of ownership | Lack of proper maintenance for implemented facility
Low community participation in project cycle | Longer time for completion of activity or less involvement of whole beneficiaries | Committee and project staff will have more workload and late completion of activities will esult low achievement of expected result | Need more time for community mobilisation and mass meeting on village development concepts
Low menpower availability (by migration) for CfW | Water supply facilities implementation can take more time than plan. Project cost may higher than expected. Market rate for casual labour may spoil. | Need more budget or implement less target | make proper plan for implementation at low job opportunity season
Poor capacity in system management
Getting approval from authorities
Community understanding in water-point site selection | Conflict of site selection for water points by technical aspect and development aspect may create misunderstanding between project and community. | Low interest / participation in project activities. | Sensative decision should be made at community mass meeting. Need to think for voting methods as some poor HH amy not articulate their need in mass meeting.
Weakness in transparency
Late implementation (need to complete before agri and livestock activity) | Agri and livestock activity will not get benefit from increase water. | Low production and will not achieve expected result of Agri and Livestock sector. | Incorporate lesson learnt from other Dry Zone programme for work plan preparation
Using appropriate technology for water supply facilty construction
Project field staff capacity on water technology | project may not have enough no. of field staff who have skill on water supply facilities construction | Low quality output on constructed water supply facilities | Prepare water supply technology documents | Select IP who has good experience / result in past project
Recruitment of quality project staff | As demand for quality project staff is high in these days, recruitment will take time. | Activities implementation can be delayed.
Data / map collection on water resources

## NUTRITION
PROBLEMS: BASIC IDENTIFICATION
What Problem? | Incidence: Who What Where is affected ? | Consequences of that Problem? | Responses? Mitigation? Treatments? | Other Aspect?
Difficult to chane from traditional water use practice to hygienic practice | Less visable outcome at early stage of the project.
Information on sanitation coverage from health department | Collected information may be different from ground. Set milestone will not be achieved. | It can make low / high achievement | Need to re-set the realistic target at end of the inception phase
Time availability of health and education staff | Can delay some activities and low achievement if project rely too much on govt. staff. | Low govt. staff involvment will effect on less sustainability. | Advocacy to decision maker at township level. Provide support facilities to govt staff who involve in project activity
Time and money for effactive IEC material production | Delay on IEC material production may cause less understand of hygiene/nutrition message.
Behaviour change | It will take more implementation time and will need significant amount of cost for behaviout change communication (BCC).
Availability of latrine water | Latrine are build but not use. So disease transmission from feces are still possible. | Diarrhoea is less control in some place | Use alternative design of latrine
Low knowledge on link between WASH and nutrition

## RESILIENCE
PROBLEMS: BASIC IDENTIFICATION
What Problem? | Incidence: Who What Where is affected ? | Consequences of that Problem? | Responses? Mitigation? Treatments? | Other Aspect?
Low coordination from Govt

## PRO POOR
PROBLEMS: BASIC IDENTIFICATION
What Problem? | Incidence: Who What Where is affected ? | Consequences of that Problem? | Responses? Mitigation? Treatments? | Other Aspect?
Linkages with national level water policy / committee
Enforcement of laws related to water

## Form
PROBLEMS: BASIC IDENTIFICATION
row | What Problem? | Incidence: Who What Where is affected ? | Consequences of that Problem? | Responses? Mitigation? Treatments? | Other Aspect? | Other Aspect?
example in row 1:
1 | Disputes about land | Former forest land, being contested by local farmers and investors / brokers from other townships; and Land authority is unable to administer | Some land un-used while some farmers are landless; low investment on used lands; conflicts over paper titles etc | LIFT avoid lands of undeclared titles? LIFT support Land authority? LIFT to support lending finance on undeclared plots?